## Sheet1
| Oct 1 - Oct 7 | Oct-8 - Oct 14 | Oct 15 - Oct 21 | Oct 22 - Oct 28 | Oct 29 - Nov 4 | Nov 5 - Nov 11 | Nov 12 - Nov 18 | Nov 19 - Nov 25 | Nov 26 - Dec 2
Data Cleaning and Preprocessing
Exploratory Data Analysis
Feature Engineering
Predictive Modeling
Data Visualization
Building Website and Integration
Basic Functionality Implementation
Additional Functionality Implementation
Deploy and Project Report